## Sheet1
HPE Production Schedule
Organization | Steps | Duration | Start Date | End Date | Notes:
Kubik/HP | provide branding guidelines and logos | 1 day | 2015-10-19 | 2015-10-19
Blue Telescope | create UX document | 2 days | 2015-10-20 | 2015-10-20
Blue Telescope | submit UX document to HP | 1 day | 2015-10-21 | 2015-10-21
Blue Telescope | create Look and Feel graphics | 3 days | 2015-10-21 | 2015-10-23
HP | provide notes on UX document | 1 day | 2015-10-22 | 2015-10-22
Blue Telescope | submit Look and Feel graphics to HP | 1 day | 2015-10-23 | 2015-10-23
HP | provide notes on Look and Feel graphics | 1 day | 2015-10-26 | 2015-10-26
Blue Telescope | programming | 17 days | 2015-10-26 | 2015-11-10
Blue Telescope | build full graphics | 3 days | 2015-10-27 | 2015-10-29
Blue Telescope | submit full screenshots to HP | 1 day | 2015-10-30 | 2015-10-30
HP | provide notes on screenshots | 1 day | 2015-11-02 | 2015-11-02
Blue Telescope | graphics revisions (as needed) | 2 days | 2015-11-03 | 2015-11-04
Blue Telescope | deliver revised screenshots to HP (as needed) | 1 day | 2015-11-05 | 2015-11-05
Blue Telescope | internal review of programming | 1 day | 2015-11-11 | 2015-11-11
Blue Telescope | programming revisions | 2 days | 2015-11-12 | 2015-11-13
Blue Telescope | internal review of programming | 1 day | 2015-11-16 | 2015-11-16
Blue Telescope | programming revisions (as needed) | 2 days | 2015-11-17 | 2015-11-18
Blue Telescope | final QA | 2 days | 2015-11-19 | 2015-11-20
Blue Telescope | deliver program to Kubik | 1 day | 2015-11-23 | 2015-11-23
Kubik | Installation and testing | 2 days | 2015-11-29 | 2015-11-30
Kubik/HP | HPE show | 3 days | 2015-12-01 | 2015-12-03